## Ark1
Gantt chart for SpaceX microsite
Project name | Project manager | Project start | Project end
Microsite SpaceX | Alida | 2019-05-13 | 2018-06-16
Tasks | Date | Days
Read through assignment | 2019-05-13 | 0.5
Research | 2019-05-13 | 0.5
Make a list of elements I want to include | 2019-05-14 | 0.5
Plan the project | 2019-05-14 | 0.5
Make functional specification | 2019-05-15 | 1
Gantt chart | 2019-05-16 | 1
Draw sketch on paper | 2019-05-18 | 1
Delivery week 1 | 2019-05-19 | 1
Target audience | 2019-05-20 | 1
Create personae and storyboards | 21.mai- 22.mai | 2
Research and make list for design/colors/typography | 23.mai- 24.mai | 2
Choose relevant API | 25.mai- 26.mai | 2
Prototype in Xd | 27.mai- 29.mai | 3
Build layout in HTML | 30.mai- 01.juni | 3
Add CSS | 02.juni- 04.juni | 3
Add content to HTML pages | 05.juni- 07.juni | 3
Finish design and mobile response in CSS | 08.juni- 09.juni | 2
Add JavaScript | 10.juni- 12.juni | 3
Testing | 2019-06-13 | 1
Set up Git repository | 2019-06-14 | 1
Write report | 2019-06-15 | 1
Delivery | 2019-06-16 | 1
Total |  | 34